Table of Contents

SIEGE OF THE BLUE WORLD

PRODUCTION ROADMAP — Plán vývoje

Verze: 0.1 (kostra)

Living document — aktualizuje se per sprint a po milnících.

## ÚVOD K DOKUMENTU

### Co tento dokument je

Production Roadmap je operativní plán vývoje hry. Obsahuje časové milníky, sprint plány, odhady, rizika, a release strategii.

### Co tento dokument NENÍ

- ❌ Designové specifikace (→ PRD, Game Bible, Tech Spec)

- ❌ Detailní technické úkoly (→ task tracker — GitHub Issues / Notion)

- ❌ Marketing plán (→ samostatný Marketing Doc)

### Cílová čtenářská skupina

- Tým — ví, co je kdy očekáváno

- Producer / lead — řízení projektu

- Stakeholders / investors (pokud bude) — milníky, deliverables

- Hráči (high-level public roadmap) — komunikace o developmentu

### Závislost na rozhodnutích

⚠ Tento dokument je závislý na uzavření Decision Logu.

Klíčová rozhodnutí, která ovlivňují roadmap: - Velikost týmu (Decision Log Q1) - Cílový hardware (Decision Log Q2) - V1 deadline (Decision Log Q10)

Bez těchto rozhodnutí je roadmap pouze odhad.

# ČÁST 1 — VYSOKÁ ÚROVEŇ

## 1.1 Project Overview

| Atribut | Hodnota |
| --- | --- |
| Project name | Siege of the Blue World |
| Genre | Singleplayer TPS Open-World RPG |
| Engine | Unity (HDRP) |
| Platform | PC (Windows) |
| Scope (long-term) | 20×20 km open world |
| Scope (V1) | Vertical slice — 1 region, 3 questy |
| Project start | [TBD — datum začátku] |
| V1 target release | [TBD — Decision Log Q10] |
| Full game target | [TBD — typicky 2-3 roky po V1] |

## 1.2 Project Phases

PHASE 0: Pre-production           [██████░░░░░░░░░░] V minulosti / now
PHASE 1: Vertical Slice (V1)      [░░░░░░░░░░░░░░░░] Next 6-12 měsíců
PHASE 2: Alpha Build               [░░░░░░░░░░░░░░░░] Po V1
PHASE 3: Beta + Polish             [░░░░░░░░░░░░░░░░] Po Alphě
PHASE 4: Release + Post-launch    [░░░░░░░░░░░░░░░░] Future

### Phase 0 — Pre-production (CURRENT)

Cíl: Mít dost dokumentace pro start tvorby.

Deliverables: - ✅ PRD v0.2 - ✅ Game Bible v0.1 - ✅ Tech Spec v0.1 - ✅ Workflow Checklist v0.2 - ✅ Lore Bible v0.1 (kostra) - ✅ Quest Design v0.1 (kostra) - ✅ Production Roadmap v0.1 (kostra) - ⚠ Decision Log uzavřený (top 10 otázek)

Milestone: “Documentation Ready for Greybox” — všechny v0.x dokumenty hotové, Decision Log top 10 uzavřený.

### Phase 1 — Vertical Slice (V1)

Cíl: Funkční prototyp s 1 regionem, 3 questy, všemi core mechanikami.

Deliverables: - Greybox (Fáze 1.5 z Workflow) - World blockout - 3 questy implementované - 4 typy nepřátel - Recon Drone Tier 1 - GPS / Tactical Map - Lethality combat - Save/Load - HDRP visual pass - Internal + external playtest

Milestone: “V1 Vertical Slice Complete” — hra je hratelná end-to-end.

### Phase 2 — Alpha Build

Cíl: Rozšířit V1 do více regionů, dokončit core systémy.

Deliverables: - 3-5 regionů - 10-15 questů - V2 features (Tier 2 drone, day/night, advanced AI) - Plný progression systém - All 15 V1 pravidel + V2 rozšíření - Internal alpha test

### Phase 3 — Beta + Polish

Cíl: Plný open world, all features, bug-free.

Deliverables: - 16-25 regionů (nebo zmenšení do realistic scope) - 30-50+ questů - Plný příběh - Polish: graphics, audio, UI - Performance optimization - Closed beta → Open beta

### Phase 4 — Release + Post-launch

Cíl: Vydat hru, post-launch support.

Deliverables: - Steam release - Day-1 patch - Post-launch content roadmap - Mod support (pokud rozhodnuto)

# ČÁST 2 — TIMELINE (Realistic Estimate)

⚠ Závislé na Decision Log Q1 (tým) a Q10 (deadline).

## 2.1 Optimistic Timeline (Tým 4-6 lidí)

[Now]                                    [V1]              [Alpha]            [Release]
  │                                        │                  │                    │
  │ ────── 6-9 měsíců ──────────────────── │ ── 9-12 m ────── │ ── 9-12 m ──────── │
  │                                        │                  │                    │
Pre-prod                              V1 done            Alpha done          Beta + Release

Total: 24-36 měsíců (2-3 roky)

## 2.2 Realistic Timeline (Tým 2-3 lidi)

[Now]                                            [V1]                  [Alpha]                [Release]
  │                                                │                      │                       │
  │ ────── 9-12 měsíců ─────────────────────────── │ ── 12-18 m ────────  │ ── 12-18 m ────────── │
  │                                                │                      │                       │
Pre-prod                                      V1 done                Alpha done             Beta + Release

Total: 36-54 měsíců (3-4.5 roku)

## 2.3 Solo Dev Timeline

[Now]                                                    [V1]                          [Alpha]
  │                                                        │                              │
  │ ────── 12-18 měsíců ─────────────────────────────────  │ ── 18-24 m ──────────────── │ 
  │                                                        │                              │
Pre-prod                                              V1 done                      Alpha done

Total V1 + Alpha: 30-42 měsíců
Full game: 5+ let (může se hodit downscale ambition)

## 2.4 Doporučený přístup

Recommendation: Solo dev na full open world je velmi ambiciózní. Doporučuji:

- Krátkodobě (Phase 0-1): Solo + AI tools je OK pro greybox a V1

- Střednědobě (Phase 2+): Hire alespoň 1 dalšího člověka (artist nebo programmer)

- Dlouhodobě (Phase 3-4): Full team nebo redukovat scope na “small open world” (5×5 km místo 20×20 km)

[Aktualizovat po Decision Log Q1]

# ČÁST 3 — SPRINT PLANNING (PHASE 1 / V1)

## 3.1 Sprint Strategy

### Sprint length

Návrh: 2-week sprints (industry standard).

Důvody: - Krátké sprinty = rychlejší feedback - 2 týdny = realistické pro indie tempo - Konzistentní cadence pro retrospektivy

### Sprint structure

Týden 1: Implementation
   Den 1: Sprint planning (1-2h)
   Den 2-5: Development
   Den 6-7: Continued dev

Týden 2: Implementation + review
   Den 8-12: Continued dev + testing
   Den 13: Sprint demo (1-2h)
   Den 14: Retrospective + next sprint plan (1-2h)

## 3.2 V1 Sprint Plan (Detail)

### Sprint 1-2: Foundation (Setup + Player + AI basics)

Goals: - Unity HDRP project setup - Folder structure, Git, naming conventions - Player Controller (movement, camera) - Basic combat (raycast pistole) - Basic AI (patrol + attack) - HP system

Deliverable: Player se hýbe, střílí, AI ho útočí. Capsule scene.

### Sprint 3-4: Combat depth (Lethality + AI cover)

Goals: - Body parts hitbox - Critical injury state - Healing animations - AI cover behavior - Sound detection system

Deliverable: Lethality combat funguje v test scéně.

### Sprint 5-6: Drone + Map

Goals: - Recon Drone Tier 1 - Camera switch mechanika - Battery system - GPS / Tactical Map basics - Heatmap rendering - Decay timer

Deliverable: Hráč může vypustit drona, vidí body na mapě.

### Sprint 7-8: Save/Load + Inventory

Goals: - Free save system - Inventory dual limit - Item categories - Loot pickup - Quest tracker UI

Deliverable: Hráč může uložit, načíst, sbírat loot.

### Sprint 9: Greybox Validation Setup

Goals: - 400m corridor scéna - 4 segmenty (les → město → modul) - Spawn points pro 4 nepřátele - 1 quest end-to-end (debug)

Deliverable: Greybox playable, ready for testing.

### Sprint 10: Greybox Testing & Iteration

Goals: - Solo playtest 3× - Iterace - External playtest 3-5 lidí - Final tweaks

Deliverable: Greybox validated, decision gate passed.

### Sprint 11-14: World Design (Blockout)

Goals: - Full V1 region blockout - 4-6 POI s konkrétními lokacemi - NavMesh setup - EMP zóny - Spawn pointy

Deliverable: Plná V1 mapa hratelná v blockoutu.

### Sprint 15-20: Quest + Enemy implementation

Goals: - Quest 1, 2, 3 implementace - Puppet/Puppeteer mechaniky - War Dog AI - Hostile humans - Crafting basic - Skill tree basic

Deliverable: All 4 enemy types + 3 questy hratelné.

### Sprint 21-24: Art Pass

Goals: - Final 3D models (environment, characters) - Animace - VFX (combat, EMP, drone) - Audio (SFX, music)

Deliverable: Visually completed V1.

### Sprint 25-26: Playtest + Polish

Goals: - Internal playtest 3× - External playtest 5-10 lidí - Bug fixes - Performance optimization

Deliverable: V1 release-ready.

### Sprint 27-28: V1 Release

Goals: - Code freeze - Final build - Internal presentation - V2 scope decisions

Deliverable: V1 VERTICAL SLICE COMPLETE

## 3.3 Total Sprint Estimate

28 sprints × 2 weeks = 56 weeks ≈ 13-14 měsíců

S buffer (industry standard +30%): ~17-18 měsíců

S team 2-3 lidí: realistic
S team 4-6 lidí: 9-12 měsíců (komprese)
S solo: 18-24 měsíců (rozšíření)

[Adjustovat po Decision Log Q1]

# ČÁST 4 — RISK ASSESSMENT

## 4.1 Technical Risks

### Risk 1: HDRP performance

Pravděpodobnost: Vysoká Dopad: Vysoký

Popis: HDRP s open-world (i 1×1 km V1) může mít FPS problémy na cílovém HW.

Mitigation: - Performance testing od Sprint 5 - LOD groups povinné - Object pooling od začátku - Backup plan: switch na URP pokud HDRP nezvládne

Status: ⚠ Active monitoring

### Risk 2: Multiplayer architecture decision later refactor

Pravděpodobnost: Středně Dopad: Vysoký

Popis: Pokud Decision Log Q3 = “passive MP-ready,” ale pak chceme aktivní MP.

Mitigation: - Rozhodni Decision Log Q3 ASAP - Architektura connectovat na začátku, ne pozdě

Status: ⚠ Pending decision

### Risk 3: Save system scope creep

Pravděpodobnost: Středně Dopad: Středně

Popis: “Free save” zní jednoduše, ale full state serialization (mapa decay, AI states, quest progress) je komplex.

Mitigation: - V1 začít s simplified save (essential state only) - Iterovat během development

Status: ⚠ Tech Spec needs detail

## 4.2 Design Risks

### Risk 4: Lethality balancing

Pravděpodobnost: Vysoká Dopad: Vysoký

Popis: Lethality combat je hard to balance — frustrating vs. enjoyable.

Mitigation: - Greybox playtest od Sprint 9 - Iterate damage thresholds (Decision Log Q4) - External playtest pro reality check

Status: 🟢 Plan in place (Greybox Phase 1.5)

### Risk 5: Multiple solutions failure

Pravděpodobnost: Středně Dopad: Vysoký

Popis: Rules-based design vyžaduje, aby všechny path options fungovaly. Pokud jedna dominuje, design fails.

Mitigation: - Quest design template (3+ paths required) - Greybox testing measures path diversity - Iterate balance per quest

Status: 🟢 Plan in place (Quest Design Doc)

### Risk 6: Lore inconsistency

Pravděpodobnost: Středně Dopad: Středně

Popis: Při expansi Lore Bible mohou vzniknout rozpory.

Mitigation: - Glosář-driven approach - Per-update consistency check - Single owner pro lore (autor)

Status: 🟢 Plan in place (Lore Bible v0.1)

## 4.3 Production Risks

### Risk 7: Solo dev burnout

Pravděpodobnost: Vysoká (pokud solo) Dopad: Catastrophic

Popis: Solo dev na ambitious project = burnout risk během 6-12 měsíců.

Mitigation: - Realistic timeline (no crunch) - Regular breaks - AI tooling pro multiplikace produktivity - Early hire, pokud financial allows

Status: ⚠ Pending Decision Log Q1

### Risk 8: Scope creep

Pravděpodobnost: Vysoká Dopad: Vysoký

Popis: Open world ambition může bobtnat (“mohli bychom přidat…”).

Mitigation: - Strict V1 scope per PRD - Decision Log explicit “out of scope” - Per-sprint scope review

Status: 🟢 Plan in place (PRD section 13)

### Risk 9: Deadline slippage

Pravděpodobnost: Vysoká (industry standard) Dopad: Středně-Vysoký

Popis: Game dev běžně překračuje deadliny o 50-100%.

Mitigation: - Buffer 30% v každém estimate - Milestone gates (no advance until current done) - Honest retrospectives

Status: 🟢 Plan in place

## 4.4 Business Risks (pokud relevantní)

### Risk 10: Funding (pokud externí)

[TBD podle Decision Log Q1]

### Risk 11: Market changes

Popis: Žánr může v 2-3 letech změnit popularity.

Mitigation: - Focus na unique features (rules-based, lethality, alien path) - Nicht hra pro stable audience (Tarkov, STALKER fans)

# ČÁST 5 — BUDGET FRAMEWORK

⚠ Závislé na Decision Log Q1.

## 5.1 Cost Categories

### Software & Licenses

| Item | Cost (yearly) |
| --- | --- |
| Unity Pro (pokud) | $185/měsíc per seat |
| Asset Store assets (V1) | $500-2000 (one-time) |
| Cloud services (Git LFS, build server) | $20-100/měsíc |
| Other software (Substance, etc.) | $50-200/měsíc |

V1 estimate: $3000-10000

### Asset purchases (V1)

| Category | Estimated cost |
| --- | --- |
| 3D environment (HDRP) | $200-1000 |
| Characters (alien, hrdina) | $100-500 |
| VFX | $100-300 |
| Audio | $200-500 |
| Music | $200-1000 |

V1 total: $800-3300

### Team costs (per Decision Log Q1)

Solo: $0 direct (opportunity cost not counted)

Tým 2-3: $5000-15000/měsíc per person - Junior: $3000-5000/měsíc - Mid: $5000-8000/měsíc - Senior: $8000-15000/měsíc

V1 timeline 12 měsíců × 3 lidi mid: ~$200-300k

### Other

- Marketing (pre-launch): $5000-50000

- Beta testing: $1000-5000

- PR / events: $2000-10000

## 5.2 Total V1 Budget Range

| Scenario | Estimate |
| --- | --- |
| Solo + minimal assets | $5,000-15,000 |
| Mikro-tým 2-3 lidi (12m) | $250,000-400,000 |
| Indie tým 4-6 (9m) | $500,000-1,000,000 |

## 5.3 Funding Strategy

[TBD podle Decision Log Q1]: - Self-funded (solo) - Bootstrapped (small team, savings) - Investors / publisher (medium-large team) - Crowdfunding (Kickstarter) - Government grants (CZ Filmový fond, regional)

# ČÁST 6 — TEAM PLAN

## 6.1 Current State

[Vyplň podle Decision Log Q1]:

Aktuální tým:
- [Tvoje jméno]: Lead designer + ?
- [TBD]: ?
- [TBD]: ?

Outsourcing:
- ?

## 6.2 Hires Needed (V1)

[Závislé na Decision Log Q1]:

| Role | When | Type | Skills required |
| --- | --- | --- | --- |
| Unity programmer | Sprint 1 (start) | Full-time / freelance | Unity HDRP, C#, AI |
| 3D artist | Sprint 11 (art pass) | Freelance | Character + environment |
| Audio designer | Sprint 21 (art pass) | Freelance | SFX + music |
| QA tester | Sprint 25 (playtest) | Volunteer / freelance | Game testing experience |

## 6.3 Onboarding Plan (per role)

### For new hires

Day 1: - Welcome + project overview (PRD) - Tooling setup (Unity, Git, task tracker) - Repo access

Week 1: - Read PRD, Game Bible, Tech Spec - Review Quest Design Doc - First task (small, low-risk)

Week 2-4: - Increasing responsibility - Sprint participation - First meaningful contribution

# ČÁST 7 — RELEASE STRATEGY

## 7.1 Target Platforms (priority order)

| Platform | When | Priority |
| --- | --- | --- |
| Steam | V1 alpha + Release | 🔴 Primary |
| GOG | Release | 🟡 Secondary |
| Epic Games Store | Post-release | 🟢 Optional |
| Console (PS5/Xbox) | Post-release V2+ | 🟢 Future |

## 7.2 Release Phases

### Pre-release

6-12 měsíců před release: - Steam page setup (basic) - Devlog začíná (YouTube, blog, X) - Community building (Discord)

3-6 měsíců před: - Closed beta - Influencer keys - Press kit - Trailer #1

1-2 měsíce před: - Open beta - Marketing push - Trailer #2 (release) - Reviews start

### Day 0 — Release

- Steam release

- Press release

- Streamers playing

- Day-1 patch ready

### Post-launch (Month 1-6)

- Monitor reviews + feedback

- Bug fix patches (weekly)

- Balance updates

- Content updates (free DLCs?)

### Long-term (Year 1+)

- V2 expansion (paid DLC)

- Community engagement

- Sale events

- Console ports (pokud rozhodnuto)

## 7.3 Pricing Strategy

[TBD]: - $19.99 — indie standard - $29.99 — mid-indie - $39.99 — premium indie - Early Access pricing (lower) → full release pricing

## 7.4 Localization Plan

[TBD podle Decision Log v0.2]:

| Language | When |
| --- | --- |
| Czech | V1 (native) |
| English | V1 (essential) |
| German, French, Spanish | Post-V1 |
| Russian, Polish | Post-V1 |
| Asian markets | V2+ |

# ČÁST 8 — KEY MILESTONES

## 8.1 Pre-production milestones

| Milestone | Status | Target Date |
| --- | --- | --- |
| Vize konsolidovaná (PRD v0.1) | ✅ Done | Apr 2026 |
| Designové filozofie (PRD v0.2) | ✅ Done | Apr 2026 |
| Documentation foundation (all v0.x) | ✅ Done | Apr 2026 |
| Decision Log top 10 closed | ⚠ Open | [TBD] |
| Engine setup + folder structure | ⚠ Open | [TBD] |

## 8.2 V1 Production milestones

| Milestone | Estimated date | Status |
| --- | --- | --- |
| M1: Core Systems Done (Sprint 8) | [Now + ~4 měsíce] | 🔘 Planned |
| M2: Greybox Validated (Sprint 10) | [Now + ~5 měsíců] | 🔘 Planned |
| M3: World Blockout Done (Sprint 14) | [Now + ~7 měsíců] | 🔘 Planned |
| M4: Quests Implemented (Sprint 20) | [Now + ~10 měsíců] | 🔘 Planned |
| M5: Art Pass Done (Sprint 24) | [Now + ~12 měsíců] | 🔘 Planned |
| M6: V1 Released (Sprint 28) | [Now + ~14 měsíců] | 🔘 Planned |

## 8.3 Post-V1 milestones

| Milestone | Estimated date | Status |
| --- | --- | --- |
| Alpha Build Complete | [V1 + 12-18m] | 🔘 Planned |
| Beta Open | [V1 + 18-24m] | 🔘 Planned |
| Full Release | [V1 + 24-36m] | 🔘 Planned |

# ČÁST 9 — TRACKING & METRICS

## 9.1 Sprint Metrics

Track each sprint: - Velocity (story points / tasks completed) - Bugs introduced vs. fixed - Documentation updates - Playtester feedback (if greybox+)

## 9.2 Project Health Metrics

Monthly: - Burndown chart (work remaining vs. timeline) - Risk register status (which risks are escalating?) - Team morale (1-10 self-report) - Quality metrics (FPS, bugs, polish %)

## 9.3 Decision Velocity

Track: - Open TBDs in PRD/Game Bible/Tech Spec - Decision Log open questions - Monthly: how many were closed?

Target: 2-5 decisions closed per month.

# ČÁST 10 — POST-LAUNCH ROADMAP

## 10.1 Month 1-3 post-launch

- Bug fixes (priority)

- Balance patches (per community feedback)

- Quality of life improvements

- Performance optimizations

## 10.2 Month 4-6

- Content updates (new questy, locations)

- Community events (developer streams, Q&A)

- Modding tools release (pokud rozhodnuto)

## 10.3 Year 1+

- Major expansion (paid DLC)

- Console ports (pokud rozhodnuto)

- Sequel pre-production (pokud project succeeds)

# CO JEŠTĚ CHYBÍ (priority pro v0.2)

## 🔴 Kritické

- Decision Log Q1, Q2, Q10 closed → tento dokument lze finalizovat

- Konkrétní team composition

- Konkrétní budget breakdown

- Konkrétní deadliny

## 🟡 Důležité

- Detail Sprint 1-10 (next 5 měsíců)

- Risk register update procedurum

- Communication plan (with stakeholders)

## 🟢 Žádoucí

- Detailní marketing plan

- Localization strategy detail

- Community management plan

- Post-launch content roadmap

# DESIGN NOTES (autoři)

## Při updatu roadmapu

✅ Aktualizuj per sprint retrospektivu (2 weeks) ✅ Aktualizuj risk register monthly ✅ Aktualizuj milestones quarterly ✅ Aktualizuj timeline po každém milestone

## Anti-patterns

❌ “Plan everything in detail upfront” (waterfall — hra dev nefunguje) ❌ “No deadlines, just vibes” (scope creep) ❌ “Hide risks until they explode” (transparency je key) ❌ “Solo dev plans like AAA studio” (unrealistic)

## Reality check otázky

Pravidelně si klást: - Děláme to, co jsme plánovali? - Plánujeme to, co bychom měli dělat? - Říkáme si pravdu o pokroku? - Měníme plán podle reality, nebo realitu podle plánu?

Production Roadmap v0.1 — Siege of the Blue World

Aktualizovat po každém sprintu a milníku.

Související dokumenty: PRD (vize), Quest Design (obsah), Decision Log (rozhodnutí).